## Sheet1
Project plan | June | [6 empty] | July | [27 empty] | August | [27 empty] | September
RPI Camera Sensor PCB | WK 4 | [6 empty] | WK 5 | [6 empty] | WK 6 | [6 empty] | WK 7 | [6 empty] | WK 8 | [6 empty] | WK 9 | [6 empty] | WK 10 | [6 empty] | WK 10 | [6 empty] | WK 11 | [6 empty] | WK 12 | [6 empty] | WK 13 | [6 empty] | WK 14 | [6 empty] | WK 15 | [6 empty] | WK 21 | [6 empty] | WK 22 | [6 empty] | WK 23
Geethan Karunaratne | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Phase 1: Background
T11: Reading Understanding Specification ( 4 hours)
T12:Setting up tools (4 hours)
T13:Assembly and integration feasiblity (10 hours)
T14:Component search (6 hours)
Phase 2: Schematic
T21:High level Schematic (4 hours)
T22:Creation of Library components for the project (6 hours)
T23:Detailed Schematic (16 hours)
M1: BOM hand off
T24:Verifying Schematic (4 hours)
M2:Schematic hand off
Phase 3: Board Design
T31:Foot print creation (10 hours)
T32:Board Design - Placement (8 hours)
T33:Board Design - Routing and DRC fixes (10 hours)
M3:Gerber Hand off
Phase 4: Testing
T41:Soldering
T42:Testing Setup (6 hours)
T43:Testing (20 hours)
M4:Verified Device Hand off